## Slide 1: Quantitative Project Management
MGT 207

## Slide 2: Idea Behind Formalizing PM
Use structure to combat scale and complexity
Make future possibilities more predictable, foresee problems, develop contingency plans
Forces us to confront things that are hard to think about in detail
  Helpful even when the details don’t unfold as expected
  Eisenhower: “The plan is nothing. Planning is everything.”
A danger—
  Structure can become an end in itself (obsession with documents, milestones)
  A distraction or (worse) a constraint on the ability to adjust plans

## Slide 3: Setting Up Project Norms
Determine how the project will operate day to day
  Set norms for meetings, updates, communication
  Establish official processes for logging, reviewing, updating progress on issues
  Set norms and escalation procedures for disagreements and unresolved issues
Important questions:
  What do we do when we encounter a new problem?
  Who do we go to for help making decisions?
  How do we check progress on a known issue?

## Slide 4: Overview
Project scheduling with known activity times
  Example
  CPM approach
Project Crashing
  Heuristic approach
Project scheduling with uncertain activity times
  PERT approach
  Simulation approach
Case study discussion

## Slide 5: Product Launch at QP Dolls, Inc.
QP Dolls, Inc. has developed a new doll it feels could turn into a “collector’s item” through proper advertising on cable TV. Product design has been done. All that remains is to plan and schedule advertising campaign and production. The company has identified 9 activities and the estimated costs for the project launch. How should it schedule the activities so that the product could be launched in the shortest time?

## Slide 6: Construction of a Network Diagram
Given:
  (1) list of all activities
  (2) precedence relationships
  (3) estimates of time and cost for each activity
We are able to construct a network diagram where:
  (1) each node represents an activity
  (2) each arc represents the precedence relationship between two activities
  (3) there is a (dummy) starting node ST and a (dummy) finishing node FIN

## Slide 7: Scheduling Calculations
After creating a network of a project, the next step in the CPM is to determine the earliest time that each activity in the network can start and finish. We determine these by what is called a forward pass.
A. Notation
  tk = estimate of the mean duration time of activity k
  ESk = earliest start time for activity k
  EFk = earliest finish time for activity k
  LSk = latest allowable start time for activity k
  LFk = latest allowable finish time for activity k
ESk | EFk
k | tk
LSk | LFk

## Slide 8: Forward Pass
B. Rules
  (1) Forward Pass (ES, EF)
  Step 1: for START node, set ESstart = 0
  Step 2: an arbitrary activity k is assumed to start as soon as
  all of its predecessor activities are completed. This may be written as:
  ESk = largest EF of activity k's predecessors =
  = the earliest possible time to start activity k
  Step 3: the earliest possible finish time of activity k is the sum of its earliest start time and the estimated activity time.
  EFk = ESk + tk

## Slide 9: Forward Pass
ST | 0
A | 6
C | 3
B | 4
E | 10
D | 3
H | 6
F | 2
G | 6
I | 8
FIN | 0

## Slide 10: Forward Pass
0 | 0
ST | 0
0 | 6
A | 6
C | 3
B | 4
E | 10
D | 3
H | 6
F | 2
G | 6
I | 8
FIN | 0

## Slide 11: Forward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
E | 10
D | 3
H | 6
F | 2
G | 6
I | 8
FIN | 0

## Slide 12: Forward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
10 | 20
E | 10
10 | 13
D | 3
10 | 16
H | 6
F | 2
G | 6
I | 8
FIN | 0

## Slide 13: Forward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
10 | 20
E | 10
10 | 13
D | 3
10 | 16
H | 6
20 | 22
F | 2
G | 6
I | 8
FIN | 0

## Slide 14: Forward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
10 | 20
E | 10
10 | 13
D | 3
10 | 16
H | 6
20 | 22
F | 2
22 | 28
G | 6
22 | 30
I | 8
FIN | 0

## Slide 15: Forward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
10 | 20
E | 10
10 | 13
D | 3
10 | 16
H | 6
20 | 22
F | 2
22 | 28
G | 6
22 | 30
I | 8
30 | 30
FIN | 0

## Slide 16: Backward Pass
  (2) Backward Pass (LS, LF)
  Step 1: LF of FINISH node is set equal to its earliest finish time as
  computed in the forward pass computations: LFFIN= EFFIN
  Step 2: the latest allowable finish time for activity k without delaying the entire project is the smallest (or earliest) of the latest allowable start times of its successor activities.
  LFk = smallest LS of k's successors =
  = latest allowable finish time for activity k without affecting the project completion time
  Step 3: the latest allowable start time for activity k without delaying the entire project is its latest allowable finish time minus the estimated activity time.
  LSk = LFk - tk

## Slide 17: Backward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
10 | 20
E | 10
10 | 13
D | 3
10 | 16
H | 6
20 | 22
F | 2
22 | 28
G | 6
24 | 30
22 | 30
I | 8
22 | 30
30 | 30
FIN | 0
30 | 30

## Slide 18: Backward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
10 | 20
E | 10
10 | 13
D | 3
10 | 16
H | 6
20 | 22
F | 2
20 | 22
22 | 28
G | 6
24 | 30
22 | 30
I | 8
22 | 30
30 | 30
FIN | 0
30 | 30

## Slide 19: Backward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
10 | 20
E | 10
10 | 20
10 | 13
D | 3
17 | 20
10 | 16
H | 6
16 | 22
20 | 22
F | 2
20 | 22
22 | 28
G | 6
24 | 30
22 | 30
I | 8
22 | 30
30 | 30
FIN | 0
30 | 30

## Slide 20: Backward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
6 | 10
B | 4
6 | 10
10 | 20
E | 10
10 | 20
10 | 13
D | 3
17 | 20
10 | 16
H | 6
16 | 22
20 | 22
F | 2
20 | 22
22 | 28
G | 6
24 | 30
22 | 30
I | 8
22 | 30
30 | 30
FIN | 0
30 | 30

## Slide 21: Backward Pass
0 | 0
ST | 0
0 | 6
A | 6
6 | 9
C | 3
7 | 10
6 | 10
B | 4
6 | 10
10 | 20
E | 10
10 | 20
10 | 13
D | 3
17 | 20
10 | 16
H | 6
16 | 22
20 | 22
F | 2
20 | 22
22 | 28
G | 6
24 | 30
22 | 30
I | 8
22 | 30
30 | 30
FIN | 0
30 | 30

## Slide 22: Backward Pass
0 | 0
ST | 0
0 | 0
0 | 6
A | 6
0 | 6
6 | 9
C | 3
7 | 10
6 | 10
B | 4
6 | 10
10 | 20
E | 10
10 | 20
10 | 13
D | 3
17 | 20
10 | 16
H | 6
16 | 22
20 | 22
F | 2
20 | 22
22 | 28
G | 6
24 | 30
22 | 30
I | 8
22 | 30
30 | 30
FIN | 0
30 | 30

## Slide 23: After Backward Pass
We know
The latest allowable starting time and the latest allowable finishing time for each activity
So…
Define Slack
SLACKk = LSk - ESk = LFk - EFk
= the length of time an activity can be delayed without affecting the completion date for the entire project, assuming all its immediate predecessors start at ES,
i.e., activity k can be delayed by SLACKk from its ESk without affecting the project completion time, assuming its successors start at the corresponding earliest allowable time

## Slide 24: Critical Path
Path
  A sequence of connected activities that leads from the START node to the FINISH node.
Critical Path (CP)
  One of the objectives of CPM is to determine the CP through a project network. The CP consists of the set of critical activities that if delayed in any way, would cause a delay in the completion of the entire project.
Clearly, critical activities are those that have zero slack…

## Slide 25: CPM: Critical Path
6 | 9
C | 3
7 | 10
10 | 13
D | 3
17 | 20
10 | 16
H | 6
16 | 22
22 | 28
G | 6
24 | 30
0
0
0
ST
0
0
6
0
6
A
6
0
10
6
4
B
10
6
20
10
10
E
20
10
22
20
2
F
22
20
30
22
8
I
30
22
30
30
0
FIN
30
30
Critical Path: Start - A - B - E - F - I - Finish

## Slide 26: Time-Cost Tradeoffs – Crashing Activities
The management of QP Dolls, Inc. is giving some thoughts to putting extra resources into the project so that it can be completed within 26 weeks. Each activity has been studied, and a set of crash times (in weeks) and cost has been developed. Determine a crash plan which minimizes the total cost of completing the project within 26 weeks.
Crashing: shortening of activity times by adding resources is referred to as crashing.
Example: Activity A would normally take 6 weeks at cost of $240,000. But Activity A can be finished in 5 weeks at cost of $300,000.

## Slide 27: A Heuristic Approach
What activities to crash and how much to crash?
Heuristic Approach
Current Critical Path: A - B - E -F- I (30 weeks)
Need completion in 26 weeks
From CPM

## Slide 28: After Crashing Activity A by 1 Week
5 | 8
C | 3
6 | 9
9 | 12
D | 3
16 | 19
9 | 15
H | 6
15 | 21
21 | 27
G | 6
23 | 29
0
0
0
ST
0
0
5
0
5
A
5
0
9
5
4
B
9
5
19
9
10
E
19
9
21
19
2
F
21
19
29
21
8
I
29
21
29
29
0
FIN
29
29
Which activity to crash next?

## Slide 29: After Crashing Activity F by 1 Week
5 | 8
C | 3
6 | 9
9 | 12
D | 3
16 | 19
9 | 15
H | 6
14 | 20
20 | 26
G | 6
22 | 28
0
0
0
ST
0
0
5
0
5
A
5
0
9
5
4
B
9
5
19
9
10
E
19
9
20
19
1
F
20
19
28
20
8
I
28
20
28
28
0
FIN
28
28
Which activity to crash next?

## Slide 30: After Crashing Activity B by 1 Week
5 | 8
C | 3
5 | 8
8 | 11
D | 3
15 | 18
8 | 14
H | 6
14 | 20
20 | 26
G | 6
21 | 27
0
0
0
ST
0
0
5
0
5
A
5
0
8
5
3
B
8
5
18
8
10
E
18
8
19
18
1
F
19
18
27
19
8
I
27
19
27
27
0
FIN
27
27
Which activity to crash next?

## Slide 31: If We Crash Activity C next…
5 | 7
C | 2
5 | 8
8 | 11
D | 3
15 | 18
8 | 14
H | 6
14 | 20
20 | 26
G | 6
21 | 27
0
0
0
ST
0
0
5
0
5
A
5
0
8
5
3
B
8
5
18
8
10
E
18
8
19
18
1
F
19
18
27
19
8
I
27
19
27
27
0
FIN
27
27
Doesn’t help.
because activity E cannot start
until both B and C finish

## Slide 32: Let Us Crash E
0 | 0
ST | 0
0 | 0
0 | 5
A | 5
0 | 5
5 | 8
C | 3
5 | 8
5 | 8
B | 3
5 | 8
8 | 17
E | 9
8 | 17
8 | 11
D | 3
14 | 17
8 | 14
H | 6
12 | 18
17 | 18
F | 1
17 | 18
18 | 24
G | 6
20 | 26
18 | 26
I | 8
18 | 26
26 | 26
FIN | 0
26 | 26
The following is the network after crashing E.
New critical paths:
A-B-E-F-I and A-C-E-F-I

## Slide 33: About Heuristic Approach
Remember:
  As you crash the current critical activities, other paths may become critical
Recommendation
  Crash activities one by one
  After crashing one activity, check the critical path(s) in the revised network

## Slide 34: Project Scheduling with Uncertain Activity Times
The designers at QP Dolls, Inc. designed a computerized doll using a completely new technology. Believing the new product is going to be a hit on market, the management wants to roll out the new product as soon as possible. However, the marketing and operations managers can only give a rough estimate (optimistic, most probable, pessimistic) on the duration time of activities for product launch. What would be the expected time required to complete the project?

## Slide 35: Three-Point Estimation Technique
A. Time estimates
  1. For each activity, estimate
    ai = optimistic time
    bi = pessimistic time
    mi = most probable time
  2. From ai, bi, and mi, compute approximate value for:
  Expected Time= μi =
  Variance = σi2 =
  Based on the assumption that the individual activity time distribution can be described by beta probability distribution
ai mi bi

## Slide 36: Critical Path & Probabilistic Analysis
B. Procedure
  1. Treat the expected activity times as the known duration of activity. Use the PERT/CPM procedure to find the critical path of the project.
  2. Compute estimates of mean and variance of project completion time as sum of expected times and variances along critical path:
  Mean (μ) = Sum of Expected Times on Critical Path
  Variance (σ2) = Sum of Variances on Critical Path
  3. Assume the project completion time is normally distributed
  N(μ, σ)
  4. Use Standardized Normal Distribution Table to determine certainty of completing project within a given time frame.

## Slide 37: QP Dolls, Inc.
0 | 0
ST | 0
0 | 0
0 | 5.83
A | 5.83
0 | 5.83
5.83 | 9.83
C | 4
8 | 12
5.83 | 12
B | 6.17
5.83 | 12
12 | 25.67
E | 13.67
12 | 25.67
12 | 17
D | 5
20.67 | 25.67
12 | 17.83
H | 5.83
22.51 | 28.34
25.67 | 27.84
F | 2.17
25.67 | 27.84
27.84 | 36.17
G | 8.33
27.84 | 36.17
27.64 | 35.67
I | 7.83
28.34 | 36.17
36.17 | 36.17
FIN | 0
36.17 | 36.17
CPM gives

## Slide 38: QP Dolls, Inc.
  Suppose the critical path is: A - B - E - F - G
  What is the estimated expected completion time?
  μCP = 5.83+6.17+13.67+2.17+8.33 = 36.17
  σCP2 = 0.25+0.69+1+0.03+1 = 2.97

## Slide 39: QP Dolls, Inc.
  (2) What is the probability of completing the project in 33 weeks?
  = NORM.DIST(33,36.17,SQRT(2.97),1) = 0.0329 or 3.3%
  (3) With 90% probability, what is the project completion time?
  = NORM.INV(0.9,36.17,SQRT(2.97)) = 38.37 days